## Start Here
Project Control Center
One workbook for the logs and trackers from Modules 2 to 6. Make one copy per project (or per company).
How to use it
1 | Save a copy and rename it, for example "Hartley Kitchen Control Center."
2 | On each tab, row 5 (or the first row under the headers) is an EXAMPLE using the practice project. Overwrite it with your own data.
3 | Type only in the blue text cells. Black cells are formulas that calculate for you, so do not type over them.
4 | Yellow cells are settings you can change, such as reminder days.
5 | Get your contractor to approve this workbook before you rely on it.
Color key
Blue text | You type here.
Black text | Formula. Leave it alone.
Yellow cell | A setting you can change.
Tabs
Bid Log | Every bid and where it stands (Module 2).
RFI Log | Questions about the drawings and their answers (Module 3).
Change Orders | Changes to the contract and the running contract total (Module 3).
Submittals | Products and samples waiting for approval (Module 3).
Permits & Inspections | Permit status and inspection dates (Module 3).
Insurance Certs | Certificate expiration dates and reminders (Module 3).
Lien Waivers | Which waiver goes with which payment (Module 3).
Materials | Promised vs needed delivery dates, with an at-risk flag (Module 4).
Receivables | Invoices sent, due, and paid (Module 6).
Job Cost | Budget vs actual and planned profit (Module 6).
Contacts | Everyone on the job (Module 5).

## Bid Log
Bid Log
Row 5 is an example. Overwrite it with your own bid.
Project | Client | Date Sent | Amount ($) | Status | Next Follow-Up | Notes | Value of open bids
Hartley kitchen remodel | Priya and Tom Hartley | 2026-03-03 | 48500 | Sent | 2026-03-06 | Confirm they received the proposal. | 48500
Bids won (count)
0

## RFI Log
RFI Log
Row 5 is an example. Overwrite it with your own RFI.
RFI # | Date | Question | From | Sent To | Needed By | Status | Answered On | Days Open
001 | 2026-05-14 | Which side of the island does the outlet go on? | Brightline Electric | Priya and Tom Hartley | 2026-05-18 | Answered | 2026-05-15 | 1
Formulas:
Days Open = IF([Date]="","",IF([Answered On]<>"",[Answered On]-[Date],TODAY()-[Date]))

## Change Orders
Change Orders
Enter the original price below. Row 8 is an example. Only changes marked "Signed" count toward the total.
Original contract price ($) | 48500
Signed change orders ($) | 1150
Current contract total ($) | 49650
CO # | Date | Description | Cost Impact ($) | Days Impact | Status | Date Signed
1 | 2026-05-20 | Change cabinet finish from white to sage green | 1150 | 5 | Signed | 2026-05-22

## Submittals
Submittals
Row 5 is an example. Overwrite it with your own submittal.
No. | Item | From | Sent To | Needed By | Status | Decision Date
001 | Quartz countertop sample | Stonecraft Surfaces | Priya and Tom Hartley | 2026-05-20 | Approved | 2026-05-19

## Permits & Inspections
Permits & Inspections
Row 5 is an example. Overwrite it with your own permit or inspection.
Item | Who Handles It | Status | Date | Notes
Building permit | Ridgeline Builders | Approved | 2026-05-12 | Post at the job site.

## Insurance Certs
Insurance Certificates
Row 5 is an example. Dates are when each policy expires.
Sub or Vendor | General Liability Expires | Workers' Comp Expires | Certificate Holder Correct? | Reminder Date | Status | Reminder days before expiry | 30
Delgado Plumbing | 2026-12-31 | 2026-12-31 | Yes | 2026-12-01 | Current
Formulas:
Reminder Date = IF(COUNT([General Liability Expires]:[Workers' Comp Expires])=0,"",MIN([General Liability Expires]:[Workers' Comp Expires])-I4)
Status = IF([Sub or Vendor]="","",IF(COUNT([General Liability Expires]:[Workers' Comp Expires])=0,"Requested",IF(MIN([General Liability Expires]:[Workers' Comp Expires])<TODAY(),"EXPIRED",IF(MIN([General Liability Expires]:[Workers' Comp Expires])-TODAY()<=I4,"Renew soon","Current"))))

## Lien Waivers
Lien Waivers
Row 5 is an example. Use the waiver forms your contractor provides.
Sub or Supplier | Payment Date | Payment Amount ($) | Waiver Type | Through Date | Waiver Received? | File Location | Waivers still missing
Delgado Plumbing | 2026-05-30 | 3600 | Unconditional progress | 2026-05-29 | Yes | 10 Billing and Lien Waivers | 0

## Materials
Materials & Deliveries
Row 5 is an example. The flag compares the promised date with the date it is needed on site.
Item | Supplier | Ordered? | Promised Date | Needed On Site | Buffer (days) | Flag | Notes | Tight if buffer is (days) or less | 3
Cabinets | Oakline Cabinets (PO 1001) | Yes | 2026-06-02 | 2026-06-08 | 6 | OK

## Receivables
Receivables
Row 5 is an example. Status and days overdue calculate from the dates.
Invoice # | Description | Amount ($) | Date Sent | Due Date | Date Paid | Status | Days Overdue | Total unpaid
002 | Progress Payment 1 and Change Order #1 | 15700 | 2026-05-30 | 2026-06-13 | 2026-06-10 | Paid |  | 0
Total overdue
0
Formulas:
Status = IF([Invoice #]="","",IF([Date Paid]<>"","Paid",IF([Due Date]="","",IF(TODAY()>[Due Date],"Overdue","Outstanding"))))
Days Overdue = IF([Status]="Overdue",TODAY()-[Due Date],"")

## Job Cost
Job Cost: Budget vs Actual
The rows shown are the practice project (original scope). Overwrite them with your own categories. Keep change order costs on their own lines.
Contract price (original scope) ($) | 48500
Total budget ($) | 40100
Planned gross profit ($) | 8400
Planned margin | 17.32%
Category | Budget ($) | Actual to Date ($) | Remaining Budget ($) | % of Budget Used
Plumbing (Delgado) | 7200 | 3600 | 3600 | 50%
Electrical (Brightline) | 6800 | 3400 | 3400 | 50%
Cabinets (Oakline) | 11200 | 11200 | 0 | 100%
Countertops (Stonecraft) | 5200 | 0 | 5200 | 0%
Tile | 1900 | 0 | 1900 | 0%
Permit and dumpster | 900 | 970 | -70 | 107.8%
Crew labor | 5400 | 3950 | 1450 | 73.15%
Materials (drywall, insulation, paint) | 1500 | 1640 | -140 | 109.3%
Total | 40100 | 24760 | 15340 | 61.75%
A negative remaining budget means that category is over budget. Job costs and profit are private: share this tab with the contractor and bookkeeper only.

## Contacts
Contacts
Row 5 is an example. Overwrite it with your own contact.
Name | Company | Role | Phone | Email | Notes
Marcus Webb | Ridgeline Builders | Owner (general contractor) | [phone] | [email] | Approves all documents before they go out.