## Invoice
PROGRESS INVOICE
Type only in the blue cells (yellow fill). Black cells calculate. The example shows Progress Payment 1 on the practice project.
Invoice details
Company | Ridgeline Builders
Invoice number | 002
Invoice date | 2026-05-30
Due date | 2026-06-13
Bill to | Priya and Tom Hartley
Project | Hartley kitchen remodel
Contract summary
Original contract price | 48500
Signed change orders to date (include any billed on this invoice) | 1150
Current contract total | 49650
Billed before this invoice | 4850
This invoice
Description | Amount
Progress Payment 1: rough inspection passed (30% of original contract) | 14550
Change Order #1: cabinet finish change | 1150
Total this invoice | 15700
Retainage percent (0% if the contract has none) | 0%
Retainage held on this invoice | 0
Net amount due now | 15700
Where the contract stands
Billed to date | 20550
Remaining balance | 29100
Retainage held before this invoice | 0
Total retainage held to date | 0
Check | OK: totals tie
Before sending: confirm the milestone is complete, every change order is signed, and your contractor has approved this invoice.
Remaining balance = current contract total minus billed to date. Try 10% in the retainage cell to see how it changes the net amount due.